## Gantt
CMSC495: Python Game Hub - Detailed Basic Gantt Chart | [19 empty] | Project Manager : | [5 empty] | Victoria Lee |  |  |  | Members: Mutry, James; Foster, Todasha; Chung, Dajin; Payne, Javon; Ipaye, Oluwatumininu
| Input column |  |  |  | Project start date: | [5 empty] | 2025-03-10 | [23 empty] | 1
Calculated column
[5 empty] | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19
 | time axis 2025-03-10 to 2025-05-09
TASK ID | Unit # Tasks per week | START DATE | WORK DAYS | END DATE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Unit 1 - Team Formation | 2025-03-10 | 10 | 2025-03-14
2 | Unit 2 - Project Plan/Code | 2025-03-15 | 3 | 2025-03-18
3 | Unit 3 - Project Plan/Code | 2025-03-18 | 5 | 2025-03-24
4 | Unit 4 - Docx/Code/Design | 2025-03-25 | 5 | 2025-03-31
5 | Unit 5 - Phase 1/Code | 2025-04-01 | 6 | 2025-04-08
6 | Unit 6 - Testing/Code | 2025-04-08 | 5 | 2025-04-14
7 | Unit 7 - Phase 2/Code | 2025-04-15 | 6 | 2025-04-22
8 | Unit 7 - Phase 2/Code 2 | 2025-04-22 | 4 | 2025-04-25
9 | Unit 8 - Final Report | 2025-04-25 | 6 | 2025-05-04 | bar: 2025-05-05
MARCH
APRIL
MAY

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (M3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TASK ID (optional), TASK NAME, START DATE, and number of WORKDAYS.
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Please do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 29), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AU-AY)
|  |  | Step 2: | Select the column after the last date (AZ), then right click and select Insert Copied Cells.
The calculation for END DATE
| • | Please do not enter the end dates manually since END DATE is a calculated column.
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.